University of Guadalajara

University Center of the Valles



|  |  |
| --- | --- |
| **School subject:** | Software Configuration Administration |
| **Professor:** | Omar Ali Zatarain Durán |

|  |  |
| --- | --- |
| **Author:** | Liusmila Nieto Cervantes |

**Contend**

[1. Definition of Baseline 3](#_Toc164372097)

[2. The configuration elements of the Baseline 4](#_Toc164372098)

[2.1 Software Requirements Specification 4](#_Toc164372099)

[2.1.1 System features 4](#_Toc164372100)

[2.1.2 Functional Requirements 4](#_Toc164372101)

[2.1.3 Non-Functional Requirements 7](#_Toc164372102)

[2.2 System Design 8](#_Toc164372103)

[2.2.1 Prototypes 8](#_Toc164372104)

[2.2.2 The architectural aspects 12](#_Toc164372105)

[2.3 Database 12](#_Toc164372106)

[2.3.1 Entity-Relationship Diagram 12](#_Toc164372107)

[2.4 Source Code 12](#_Toc164372108)

[2.5 Acceptance Testing Design 12](#_Toc164372109)

[3. Configuration Control 13](#_Toc164372110)

[3.1 Decision Making Policy 13](#_Toc164372111)

[3.1.1 Authority and Responsibilities 13](#_Toc164372112)

[3.1.2 Decision Making Process 14](#_Toc164372113)

[3.1.3 Decision making criteria 15](#_Toc164372114)

[3.1.4 Evaluation of Change Request 17](#_Toc164372115)

[3.1.5 Process for the Implementation of the Change Request 19](#_Toc164372116)

[3.1.6 Evaluation variables to measure the behavior of the implemented change. 20](#_Toc164372117)

[4. Status accounting 23](#_Toc164372118)

[4.2 Policies for monitoring and evaluation status accounting 23](#_Toc164372119)

[5. Change Requests 24](#_Toc164372120)

[5.1 Change request #1 24](#_Toc164372121)

[5.1.1 Strategic Evaluation 24](#_Toc164372122)

[5.1.2 Technical Evaluation 25](#_Toc164372123)

[5.1.3 Evaluation of Change Request 27](#_Toc164372124)

1. Definition of Baseline

A baseline provides a logical basis for comparison. A specific version of a single work product by itself, or a set of work products together can be established as a baseline. During the course of product development, a series of baselines is established, enabling assessment of the evolving product’s maturity at different points in time.

The baseline is established for the development project "Information Management System for the Laboratory of Psychological Attention and Intervention (LPAI) in the University Centers ".

The development of the management system is done using the Extreme Programming (XP) methodology. The configuration elements that form the baseline are defined in accordance with the artifacts proposed by this methodology.

* **Software Requirements Specification**
  + Functional Requirements and Non-Functional Requirements)

The software to be developed is described based on an understanding of the business context and analysis of the main characteristics.

* **System Design** (Prototypes and Architectural Aspects).
  + Prototypes are created for a better understanding of functional requirements.
  + The architectural aspects of the system are described according to the framework to be used.
* **Database**.
  + Entity-Relationship Diagram is performed to design and understand the architecture of the database.
* **Source Code**.

Source code obtained as a result of the implementation process.

* **Acceptance Testing Design**.

It includes the test cases and acceptance criteria that will be used to validate whether the system meets the requirements and expectations of the customer.

2. The configuration elements of the Baseline

2.1 Software Requirements Specification

2.1.1 System features

To contribute to the management and control of the information generated in the LPAI, a computer system will be developed for its information management. This system will allow standardized management of the information, contributing to its integrity, availability, and redundancy.

The modules defined for the system are:

|  |  |
| --- | --- |
| **Module** | **Description** |
| Security | It will include functions for user management and user permission. |
| Management of Nomenclatures | It includes options to define standardized information in the system (nomenclatures). |
| Management of Laboratories LPAI | This module will allow the management of LPAI laboratories located in various universities, providing functions to list, add, modify and delete information from the laboratories. |
| Psychological Assessment and Follow-up | It will conduct psychological assessments and will allow for the recording of the follow-up on the provided psychological attention. |
| Reports | It provides information about the number of patients attended and evaluated based on their academic degree and the type of care received, allowing tracking of the laboratory's activity. |

2.1.2 Functional Requirements

**Module Security:**

FR1: List users.

FR2: Add user.

FR3: View data from user.

FR4: Update user data.

FR5: Delete user.

FR6: Assign role to user.

FR7: Authenticate user.

FR8: Modify user password.

**Module Management of Nomenclatures:**

FR1: List Bachelor's Degree.

FR2: Add Bachelor's Degree.

FR3: View data from Bachelor's Degree.

FR4: Update Bachelor's Degree.

FR5: Delete Bachelor's Degree.

FR6: List Degree.

FR7: Add Degree.

FR8: View data from Degree.

FR9: Update Degree.

FR10: Delete Degree.

FR11: List Family Income.

FR12: Add Family Income.

FR13: View data from Family Income.

FR14: Update Family Income.

FR15: Delete Family Income.

FR16: List Institutions of Psychological Attention.

FR17: Add Institutions of Psychological Attention.

FR18: View data from Institutions of Psychological Attention.

FR19: Update Institutions of Psychological Attention.

FR20: Delete Institutions of Psychological Attention.

**Module Management of Laboratories LPAI:**

FR1: List Laboratories LPAI.

FR2: Add Laboratories LPAI.

FR3: View data from Laboratories LPAI.

FR4: Update Laboratories LPAI.

FR5: Delete Laboratories LPAI.

**Module Psychological Assessment and Follow-up:**

FR1: List Psychological Attention.

FR2: Add a Psychological Attention.

FR3: View data from Psychological Attention.

FR4: Update Psychological Attention data.

FR5: Register Psychological Instruments “Measures of Transversal Symptoms (MST)” applied to the patient.

FR6: Generate patient assessment based on the psychological instrument applied.

FR7: View data from Psychological Instruments MST.

FR8: Update Psychological Instruments MST.

FR9: Register Type of Attention indicated to the patient (Refer, Workshops, Consultations).

FR10: Register Patient Attention Status (Follow-up, Discharge, Discontinuation).

**Module Reports:**

FR1: Generate a report with the total number of patients attended per Bachelor of a University Center.

FR2: Generate reports with the total number of patients attended by Specialists at a University Center.

FR3: Generate a report with the total number of patients evaluated by Type of Attention of all University Centers.

FR4: Generate a report with the total number of patients by their Attention Status of all University Centers.

2.1.3 Non-Functional Requirements

**Security:**

* + A two-factor authentication system must be implemented to access the system.
  + All confidential data must be stored using encryption techniques.
  + Users of each Laboratory should only see the information of the patients associated with it.

**Graphic Design:**

* + The user interface must follow responsive design guidelines to adapt to different devices and screen sizes.
  + A color palette based on light blues should be used.

**Availability:**

* + An automated backup system must be implemented to perform daily backups.
  + Planned maintenance must be carried out during low-demand hours.

**Portability:**

* + The system must be compatible with web browsers such as Chrome, Firefox, Safari, and Internet Explorer.
  + The system must be compatible with multiple operating systems, such as Windows, MacOS, and Linux.

2.2 System Design


2.2.1 Prototypes

The prototypes of User Stories with High priority are presented, taking into account their complexity and importance to the clients.

The prototype information is written in Spanish, as the system will be developed for University Centers in Mexico, where the native language is Spanish.

**Module Security:**

UH1: List users.




UH2: Add user.

|  |  |
| --- | --- |
|  |  |


**Module Management of Nomenclatures:**

UH1: List Nomenclatures (Bachelor's Degree, Degree, Family Income, Institutions of Psychological Attention).



**Module Management of Laboratories LPAI:**

FR1: List Laboratories LPAI.



**Module Psychological Assessment and Follow-up:**


UH1: List Psychological Attention.



UH2: Register Type of Attention indicated to the patient (Refer, Workshops, Consultations).



UH3: Register Patient Attention Status (Follow-up, Discharge, Discontinuation).




**Module Reports:**

UH1: Generate a report with the total number of patients attended per Bachelor of a University Center.

UH2: Generate reports with the total number of patients attended by Specialists at a University Center.

UH3: Generate a report with the total number of patients evaluated by Type of Attention of all University Centers.

UH4: Generate a report with the total number of patients by their Attention Status of all University Centers.



|  |  |
| --- | --- |
|  |  |
|  |  |
|  |  |

2.2.2 The architectural aspects

2.3 Database

2.3.1 Entity-Relationship Diagram

2.4 Source Code

2.5 Acceptance Testing Design

3. Software Configuration Control

This section describes the process for managing changes in the configuration and deviations from the defined baseline. Procedures are established to control and track the implementation of these changes.

3.1 Decision Making Policy

The decision-making policy in configuration control of a project is fundamental to establish a framework for decision-making related to change requests. This policy defines who has the authority to approve or reject changes, how proposed changes are evaluated, and what criteria are used for decision making.

3.1.1 Authority and Responsibilities

* Define who has the authority to approve or reject changes in the system configuration.
* Assign clear responsibilities to each team member regarding the submission and evaluation of changes.

|  |  |
| --- | --- |
| **Committee Change Control** | |
| **Rols** | **Responsibilities** |
| Manager |  |
| Project Manager | * Coordinate committee meetings and ensure that established objectives are met. * Responsible for presenting and coordinating the evaluation of changes. |
| Technical Leader | * Provides technical advice on the feasibility and impact of proposed changes on system functionalities, architecture, and quality assurance. |
| Human Resources Manager | * Assess the impact of changes on personnel and organizational structure. * Provide recommendations on how to manage any impact on the project's human team (e.g., new staff hiring or management of staff overtime hours). |
| Finance Manager | * Assess the impact of changes on monetary cost and determine their financial feasibility. |

3.1.2 Decision Making Process

Below is detailed how the decision-making process for change requests is carried out. The responsibilities of each member of the change control board in decision-making are included.

|  |  |  |
| --- | --- | --- |
| **Activities** | | **Rol** |
| 1 | * Submit Request | * Client * Stakeholder * Project Team |
| 2 | * Review the request and decide whether to record it as a change request * Register the request, if you decided it is a change request. | * Project Manager |
| 3 | * Initially assess the change request to determine its feasibility and relevance, ensuring understanding of its scope and potential impact. | * Project Manager |
| 4 | * Present the change request to the committee for to start your evaluation. | * Project Manager |
| 5 | Strategic Evaluation:   * Develop the SWOT Matrix corresponding to the change request. * Evaluate the strategic impact of the change in terms of business objectives, budget, necessary personnel, and deadlines for fulfilling the change request. | * Project Manager * Human Resources Manager * Finance Manager |
| 6 | Technical Evaluation:   * Assess the technical feasibility of the change and its impact on the existing architecture and design. * Determine if new tools or technologies are needed to implement the proposed change. | * Technical Leader |
| 7 | Reviewing and Discussion of Change Requests in the Committee:   * Review and discuss the change request in detail, considering the technical and strategic analyses previously conducted. | * Committee Change Control |
| 8 | Decision Making:   * Make a decision regarding the change request, considering the recommendations and opinions gathered. | * Committee Change Control |
| 9 | Documentation and Communication of Decisions:   * Document the decision made during the committee meeting. * Communicate the decision to all relevant stakeholders. | * Project Manager |
| 10 | Follow-up and Implementation Supervision:   * Supervise the implementation of the change (if approved), ensuring it is carried out as planned and objectives are achieved. | * Project Manager |

3.1.3 Decision making criteria

The decision-making process in a project is based on key criteria that guide the evaluation of proposed changes. These aspects are fundamental to ensure that the decisions made are aligned with the project's objectives.

1. **Impact on the business**:
   * High: If the proposed change has a significant impact on the business's objectives and goals, such as improving process efficiency, increasing revenue, or meeting customer needs. For example: The change involves adding a new feature that will significantly enhance the customer experience and increase customer retention.
   * Medium: If the change has a moderate impact on the business, such as improving internal processes or increasing team productivity. For example: The addition of a functionality that allows better process management and resource allocation to improve productivity, but does not introduce changes in the execution of business processes.
   * Low: If the change has a limited impact on the business and only affects minor aspects of the processes. For example: Changing graphic design elements (iconography, colors, informative texts) in the user interface that do not have a significant impact on the final business outcomes.
2. **Urgency of change:**
   * High: If the change involves complex modifications to the architecture or design of the system, requires the development of new complex functionalities, or affects critical areas of the system. For example, the change involves integrating a new complex technology that requires significant changes to the system's architecture.
   * Medium: If the change is important but not critical, and can wait for a reasonable period before being implemented.
   * Low: If the change is desirable but not urgent, and can be addressed in the future without causing immediate problems.
3. **Technical Complexity:**
   * High: If the change involves complex modifications to the architecture or design of the system, requires the development of new complex functionalities, or affects critical areas of the system. For example, the change involves integrating a new complex technology that requires significant changes to the system's architecture.
   * Medium: If the change involves some technical complexity but can be addressed with resources and technical skills available within the team.
   * Low: If the change is relatively simple and does not require significant modifications to the existing infrastructure or design.
4. **Cost Associated:**
   * High: If the change entails a high direct and indirect cost, which may include significant expenses for human resources, materials, and time. For example: Acquiring new software licenses and hiring additional staff for its implementation are required.
     + Additional Cost: Greater than or equal to 50% of the initial cost.
     + Additional time: Greater than or equal to 50% of the initial time.
   * Medium: If the change has a moderate cost and can be financed within the allocated project budget. For example: It involves updating existing hardware and software to ensure compatibility with new technology, which will incur a moderate but manageable cost within the assigned budget.
     + Additional Cost: Greater than or equal to 25% and less than or equal to 49% of the initial cost.
     + Additional Time: Greater than or equal to 25% and less than or equal to 49% of the initial Time.
   * Low: If the change has a low cost and can be implemented without requiring significant financial investment. For example, updating minor text elements in the user interface, which can be easily done with existing resources and tools, without incurring additional expenses.
     + Additional Cost: Less than 25% of the initial cost.
     + Additional Time: Less than 25% of the initial time.

3.1.4 Evaluation of Change Request

For the evaluation of the change, a scale based on an ordinal structure is used, where numerical values are sequentially assigned (preferably odd numbers) to reflect the relative order of the levels of each criterion. The evaluation considers different levels of impact on the business, urgency of change, technical complexity, and associated cost.

|  |  |  |  |
| --- | --- | --- | --- |
| **Criteria** | **Levels** | | |
| **High** | **Medium** | **Low** |
| Impact on the business | 4-5 | 2-3 | 0-1 |
| The more positive impact it has on the business, the higher the score it receives. | | |
| Urgency of change | 4-5 | 2-3 | 0-1 |
| The more urgency for implementation it has, the higher the score it receives. | | |
| Technical Complexity | 0-1 | 2-3 | 4-5 |
| The more technical complexity the implementation of the change has, the lower the score it receives. | | |
| Cost Associated | 0-1 | 2-3 | 4-5 |
| The more costs the implementation of the change has, the lower the score it receives. | | |

If the sum of the scores is:

* Greater than or equal to 15: The change can be **approved**.
* Between 8 and 14: **Additional assessment** is required before making a decision.
* Less than or equal to 7: The change must be **rejected**.

Note: Lower scores are assigned to changes with higher technical impact and associated costs, better reflecting their high risk and the need for a more detailed review or even rejection of the change if the sum of the scores is sufficiently low.

Defined subprocess for when the change evaluation score falls within the range of 8 to 14 (**Additional assessment**).

|  |  |  |  |
| --- | --- | --- | --- |
| **Activities** | | **Rol** | |
| 1 | Prepare a detailed report with the results of the initial evaluation of the proposed change, including the criteria of impact on the business, urgency of the change, technical complexity, and associated cost. | | * Project Manager |
| 2 | Analyze the report with the details of the initial evaluation.   * The criteria of "Impact on the business" and "Cost Associated" are analyzed. | | * Manager * Project Manager |
| 3 | Make the final decision on the approval or rejection of the change, based on the information presented.   |  |  |  | | --- | --- | --- | | Decision | Impact on the business | Cost Associated | | Approve | Alto | Medio o Bajo | | Medio | Bajo | | Bajo | Bajo | | Reject | Alto | Alto | | Medio | Alto | | Bajo | Alto o Medio | | | * Manager |
| 4 | Communicate the final decision to all relevant stakeholders, including the project team and the change control committee. | | * Project Manager |

3.1.5 Process for the Implementation of the Change Request

|  |  |  |
| --- | --- | --- |
| **Activities** | | **Rol** |
| 1 | Analysis and Planning of Change Implementation. | |
| * Analyze the change request in detail to understand its requirements and the impact on the system. | * Analysts of Requirements. * Architect |
| * Establish a detailed plan for change implementation, including the necessary human, material, and technological resources, as well as the corresponding schedule of activities. | * Project Manager |
| 2 | Implementation of Corresponding Modifications. | |
| * Implement the specific tasks planned to carry out the modifications corresponding to the change request. | * Developers |
| 3 | Validation Testing. | |
| * Perform tests to verify the integrity and functionality of the system with the newly implemented modifications. | * Testers |
| * Conduct integration tests to ensure that the new functionalities integrate seamlessly with the existing system. |
| 4 | Communication of Implemented Change. | |
| * Inform affected users about the implemented change through meetings or other communication channels. | * Project Manager |
| 5 | Training and Preparedness for the Implemented Change.   * Note: This activity is carried out if the system is already being used by users. | |
| * Plan training sessions for users who will utilize the new system functionalities. | * Training Team |
| * Develop training materials to assist users in understanding the change. |
| 6 | Closure of Change Request. | |
| * Inform all stakeholders that the change request is officially closed. | * Project Manager |
| * Conduct a final evaluation of the implemented change to gather feedback from end users and other stakeholders (e.g., Satisfaction surveys). |

3.1.6 Evaluation variables to measure the behavior of the implemented change.

1. **Adherence to Schedule.** 
   * It evaluates whether the implementation of the change is carried out within the planned time frame. It is measured by comparing the actual start and end dates of each activity with the planned dates.
   * Actions to be taken based on the variable measurement.

* Within Schedule: No additional actions are required. Project tracking continues as usual.
* Schedule Delay: Identify the causes of the delay and take corrective actions, such as allocating more resources, reorganizing tasks, or reviewing the planning to recover lost time.
* Schedule Advance: Make adjustments to the planning to take advantage of the advance or redistribute resources as necessary.

1. **Cost Efficiency.**
   * It evaluates how the implementation of the change affects the project budget. It is measured by comparing the actual costs with the budgeted costs for implementing the change.
   * Actions to be taken based on the variable measurement.
     + Within Budget: No additional actions are required. Monitoring of costs continues to keep them within the budget.
     + Cost Below Budget: Evaluate if there are areas where the remaining budget can be reinvested to enhance the project or adjust the planning to utilize available resources more efficiently.
     + Cost Above Budget: Identify the reasons for the overage and take corrective actions. Efforts should be made to reduce costs or renegotiate contracts as necessary.
2. **Impact on System Quality.**
   * It evaluates how the implementation of the change affects the system's performance in terms of functionality and stability. It is measured through technical tests that assess the system before and after the change implementation. The correctness and completeness of functionalities and the error rate before and after the change request are analyzed.
   * Actions to be taken based on the variable measurement.
     + Quality values maintained: Continue monitoring the quality of the system.
     + Quality values decrease: Identify areas where deficiencies and provide additional training to the team or make improvements to the infrastructure.
     + Quality values increase: Implement de best practices identified in other aspects of the project and celebrate achievements with the team and stakeholders.
3. **Impact on Risk Management.**
   * It evaluates how the implementation of the change affects the system's risks management. It is measured comparing the risk management before and after the change.
   * Actions to be taken based on the variable measurement.
     + If the same risks persist: Continue monitoring and updating the project's risk management.
     + If risks increase: Identify areas where risks have increased and take corrective actions (review the risk management process in detail).
     + If risks decrease: Identify the best practices that contributed to this decrease and apply them in other areas of the project.

4. Status accounting

Status accounting is an important process in project management that involves the recording, tracking, and documentation of the current state of relevant project aspects.

4.1 Policies for monitoring and evaluation status accounting

The policies for monitoring and evaluation status accounting are fundamental to ensure that a project is aligned with its objectives and to identify areas for improvement.

Variables to consider in the current project status accounting process:

1. **Project Progress.**
   * + Variable: Task Progress.

Provides an overview of how much work has been completed compared to the total planned work. It allows evaluating whether the objectives are being met within the scheduled timeframe.

How to measure the variable?

Assess the project's progress compared to the planned schedule.

* Calculate the percentage of elapsed time (in days) from the start of the project to the current moment, in relation to the total duration. Percentage of elapsed time = (Elapsed time since the start of the project / Total duration of the project) \* 100.
* Calculate the percentage of completed tasks: (number of tasks completed / total number of planned tasks) \* 100.
* Compare the elapsed time with the percentage of tasks completed to determine if the project is on schedule or delayed.

Task Progress Evaluation.

* On Schedule: If the progress percentage is equal to or greater than (>=) the percentage of elapsed time.
* Delayed: If the progress percentage is less (<) than the percentage of elapsed time. Measures should be taken to recover lost time.
* Ahead of Schedule: If the progress percentage is greater (>) than the percentage of time elapsed. There may be opportunities to improve efficiency or add more features.
  + - Variable: Milestone Achievement.

Evaluates milestone completion to verify if key points are being achieved as scheduled in the timeline. It monitors that objectives are being reached within the established deadlines.

How to measure the variable?

Verify if the milestones are being met and if the progress is in line with the schedule.

* Compare the achievement date of each milestone with the planned date, determining if they are being met on time.

Milestone Achievement Evaluation.

* On Time: All milestones are completed on or before the planned date.
* Delayed: At least one milestone has an achievement date later than the planned date.
* Ahead of Schedule: All milestones are completed before the planned date.

1. **Budget.**

Variable: Expenditure Monitoring

This involves keeping track of project expenses to ensure they stay within the allocated budget.

How to measure the variable?

* Compare the expenses with the budgeted costs for the project phases analyzed in the evaluation.

Budget Evaluation.

* Within Budget: If actual costs remain within the allocated budget for the analyzed phase of the project.
* Over Budget: If actual costs exceed the allocated budget for the phase. Measures should be taken to control costs and prevent overruns.
* Below Budget: If actual costs are lower than the allocated budget for the phase.

1. **Risks.**

Variable: Risk Impact

Monitor and evaluate the risks identified during the project to ensure they are being managed correctly and anticipate potential future issues.

How to measure the variable?

* Count the number of mitigated risks from the beginning of the project until the current moment.
* Count the number of new risks that have emerged during the project.

Risk Impact Evaluation.

* Low Incidence: If the number of mitigated risks is significantly greater than the number of new risks that have emerged.
* Moderate Incidence: If the number of mitigated risks is approximately equal to the number of new risks that have emerged.
* High Incidence: If the number of new risks that have emerged is significantly greater than the number of mitigated risks.

5. Change Requests

5.1 Change request #1

The client wants to make profit from the system you are developing. He requested that the system should have a module that retrieves the statistics from a series of branches across the country.

5.1.1 Strategic Evaluation

The SWOT matrix is used to identify and assess the Strengths, Weaknesses, Opportunities, and Threats associated with the change request. The matrix provides a comprehensive view of the internal and external factors that may influence the success of the change request implementation.

|  |  |
| --- | --- |
| STRENGTHS (+)   * Team experience in report module development. * The system allows for the addition of new modules, as the Django Framework architecture makes it flexible and scalable. * Statistics in the psychological care sector have a growing demand and are necessary for research purposes. | WEAKNESSES (-)   * Increased project cost and duration due to the change. * Introduction of errors in already implemented modules due to the addition of new functionalities that involve changes in them. |
| OPPORTUNITIES (+)   * Contribute to decision-making for laboratory management, improving the effectiveness of psychological services provided to the university community | THREATS (-)   * Regulatory changes in psychological care and intervention that could affect the information associated with the generation of statistics. |

5.1.2 Technical Evaluation

The change request affects the following configuration items:

1. The Requirements Specification Document: new functionalities will be added (Obtaining statistics associated with types of attention and patient follow-up).
   * + A module was added: “Management of Laboratories LPAI”. This module contains 5 functional requirements (list, add, modify and delete information from the laboratories).
     + The "Reports" module was modified. The scope of the functional requirement "FR3" was modified (the quantity must be obtained for all University Centers) and a new functional requirement "FR4" was added (the total number of patients by their Attention Status of all University Centers).
2. The System Design Document: new classes must be created for subsequent implementation.
3. Source code: New classes with their methods must be implemented.
4. Database: New tables and their relationships. Implement new procedures to obtain the new reports.
5. Acceptance Testing Document: New test cases must be designed to validate the new functionalities.

This change impacts the baseline, causing an impact on the duration and final cost of the project.

* The duration of the project will be extended by 1 month (20 Work days).
  + Initial duration of the project: 4 months (80 Work days).
  + Additional time: 1 month (Represents **25%** of the initial duration).
  + Current project duration: 4 months + 1 month = **5 months (100 Work days).**

The following table details the calculation of the time necessary to develop Change Request #1.

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Functionalities** | **Requirements Specification Document** | **System Design Document** | **Database** | **Source code** | **Acceptance Testing Document** |
| **Time (Days)** | | | | |
| Module Management of Laboratories LPAI  (Add 5 functional requirement) | 1 | 2 | 1 | 4 | 2 |
| Module Reports  (Modified FR3) | 1 | 1 | 2 |
| Module Reports  (Add FR4) | 1 | 1 | 4 |
| **Change request #1** | 1 | 4 | 3 | 10 | 2 |
| **20 Days**  **(1 month)** | | | | |

* The cost of the project will increase, it is necessary to pay 1 more month of work to the team.
  + Initial project cost: 235680 MXN.
  + Additional cost: 58920 MXN (Represents **25%** of the initial cost).
  + Current project cost: 235680 MXN + 58920 MXN = **294600 MXN**.

The following tables detail the additional cost calculation associated with Change Request #1.

|  |  |  |  |
| --- | --- | --- | --- |
| **Roles** | **Configuration items** | **Daily Salary  (Mexican coin)** | **Change request #1 (Days - Salary)** |
| Analyst | Requirements Specification Document | 2000 MXN | 1 Day  2000 MXN |
| Architect | System Design Document | 2700 MXN | 4 Days  10800 MXN |
| Developer | Database, Source code | 2500 MXN | 13 Days  32500 MXN |
| Tester | Acceptance Testing Document | 1900 MXN | 2 Days  3800 MXN |
| Total Salary | | | 49100 MXN |
| 20 %  Other expenses (Electricity, Rent, Office Supplies and other expenses) | | | 9820 MXN |
| **Total Additional Cost** | | | **58920 MXN** |

5.1.3 Evaluation of Change Request

|  |  |  |
| --- | --- | --- |
| **Criteria** | **Levels** | **Evaluation** |
| Impact on the business | High (5) | Sum: 16  **Approved** |
| The requested change request could assist the client in making strategic decisions regarding the performance of all laboratories, thereby enhancing the efficiency of psychological care and having a greater impact on the university community. |
| Urgency of change | High (5) |
| The requested change must be implemented as soon as possible since the system needs to be adapted to accommodate multiple configured laboratories. Additionally, these statistics are crucial in the decision-making process for the management team. |
| Technical Complexity | Medium (3) |
| The change will be addressed with the current human resources of the team, and there is no need to purchase or learn new technologies to implement it, only more development time is required.  The change request involves adding a new module for laboratory management, which causes moderate changes in some system modules and modifications to the database. Additionally, two new statistics associated with the change request need to be implemented. The changes do not make modifications to the defined architecture or significant changes to existing modules. |
| Cost Associated | Medium (3) |
| Represents 25% of the initial cost.   * Initial project cost: 235680 MXN * Additional cost: 58920 MXN   Represents 25% of the initial duration.   * Initial project duration: 5 months * Additional time: 1 month |

5.2 Change request #2

The government launched a new system to collect information on the statistics of mental disorders. For this purpose, the system should generate reports by psychologists with the number of patients, types of disorders, and treatment time. The reports should be formatted according to the new system, and an authentication method using a Kerberos-like system should be implemented to avoid information leakage. The reports should be released weekly and monthly.

5.2.1 Strategic Evaluation

The SWOT matrix is used to identify and assess the Strengths, Weaknesses, Opportunities, and Threats associated with the change request. The matrix provides a comprehensive view of the internal and external factors that may influence the success of the change request implementation.

|  |  |
| --- | --- |
| STRENGTHS (+)   * Team experience in report module development. * The system allows for the addition of new modules, as the Django Framework architecture makes it flexible and scalable. * Potential to enhance the system's reputation with the government and other institutions by complying with their new regulations. | WEAKNESSES (-)   * The development team lacks knowledge of the Kerberos authentication method. * Although the implementation of a Kerberos-like authentication method is mentioned, ensuring the complete security of sensitive data is a challenge. |
| OPPORTUNITIES (+)   * Obtaining new reports opens new avenues for mental health research, including the development of new treatments and therapies. * Contributing to the development of more effective mental health policies through accurate and updated data. | THREATS (-)   * Since the reports will be generated for the government, there is a risk of being targeted by hackers seeking access to sensitive information. * Laws and regulations related to privacy and data protection may change, which could require significant adjustments to the system. |

5.2.2 Technical Evaluation

The change request affects the following configuration items:

1. Requirements Specification Document:
   * New functionalities will be added (Obtaining statistics associated with mental disorders (number of patients, types of disorders, and treatment time)).
   * The module associated with System Security will be modified, specifically the authentication method, which should be implemented similar to the Kerberos method.
2. Source Code: new classes with their methods must be implemented.
3. Database: new stored procedures must be implemented to obtain the new reports.
4. Acceptance Testing Document: new test cases must be designed to validate the new functionalities related to the statistics of mental disorders and the new authentication method.

This change impacts the baseline, causing an impact on the duration and final cost of the project.

* The duration of the project will be extended by 2 weeks (10 Work days).
  + Initial duration after accepted Change Request #1: 5 months (100 working days).
  + Additional time: 10 days (Represents **10%** of the initial duration).
  + Current project duration: 5 months + 0.5 months = **5.5 months (110 Work days).**

The following table details the calculation of the time needed to develop Change Request #2.

* The implementation of the statistics on mental disorders and the adjustment of the authentication method will be done in parallel.
* The implementation of the statistics on mental disorders will be carried out by the project development team.
* For the analysis, design, implementation and testing of authentication settings similar to Kerberos, the service of an external company will be contracted.

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Functionalities** | **Requirements Specification Document** | **System Design Document** | **Source code** | **Acceptance Testing Document** | **Days**  **for functionality** |
| **Time (Days)** | | | |
| Module Reports (Obtain statistics on mental disorders) | 2 | 1 | 5 | 2 | 10 |
| Module Security  (Adjust the implementation of System authentication to be similar to the Kerberos method) | The external company will plan its service adjusted to 10 days. | | | | 10 |
| **Change request #1** | **10 Days**  **(2 weeks)** | | | | |

* The cost of the project will increase, it is necessary to pay 10 more days of work to the team and contract the services of an external company.
  + Initial project cost after accepted change request #1: 294600 MXN.
  + Additional cost: 59600 MXN (Represents **20%** of the initial cost).
    - 27 600 MXN: Cost of developing statistics on mental disorders.
    - 32000 MXN: Cost of hiring the external company to make adjustments in the authentication method.
  + Current project cost: 294600 MXN + 59600MXN = **354200 MXN**.

The following tables detail the additional cost calculation associated with Change Request #2.

|  |  |  |  |
| --- | --- | --- | --- |
| **Roles** | **Configuration items** | **Daily Salary  (Mexican coin)** | **Change request #1 (Days - Salary)** |
| Analyst | Requirements Specification Document | 2000 MXN | 2 Day  4000 MXN |
| Architect | System Design Document | 2700 MXN | 1 Days  2700 MXN |
| Developer | Source code | 2500 MXN | 5 Days  12500 MXN |
| Tester | Acceptance Testing Document | 1900 MXN | 2 Days  3800 MXN |
| Total Salary | | | 23000 MXN |
| 20 %  Other expenses (Electricity, Rent, Office Supplies and other expenses) | | | 4600 MXN |
| **Total Additional Cost** | | | **27600 MXN** |

5.2.3 Evaluation of Change Request

|  |  |  |
| --- | --- | --- |
| **Criteria** | **Levels** | **Evaluation** |
| Impact on the business | High (5) | Sum: 12  **Additional assessment** |
| The change request enhances the system's reputation by complying with new government regulations and provides crucial data for mental health research. |
| Urgency of change | Medium (2) |
| Although it is important to comply with new government regulations, its implementation is not immediately urgent. |
| Technical Complexity | High (1) |
| Implementing a Kerberos-like authentication method is technically challenging. Kerberos is a complex protocol that requires a deep understanding of security. |
| Cost Associated | Low (4) |
| Represents 20% of the initial cost.   * Initial project cost after accepted change request #1: 294600 MXN * Additional cost: 59600 MXN   Represents 10% of the initial duration.   * Initial duration after acceptance of change request #1: 5 months * Additional time: 0.5 months |

The initial assessment of the change request, starting from the scale defined in the process, led to an additional assessment of the change. This evaluation is detailed below.

|  |  |  |
| --- | --- | --- |
| **Decision** | **Impact on the business** | **Cost Associated** |
| **Approve** | Alto | Bajo |

5.3 Change request #3

The client requests that the screens used throughout the system be modified for people with visual impairments. It includes the change of fonts, colors, and descriptions with sound besides text descriptions.

5.3.1 Strategic Evaluation

The SWOT matrix is used to identify and assess the Strengths, Weaknesses, Opportunities, and Threats associated with the change request. The matrix provides a comprehensive view of the internal and external factors that may influence the success of the change request implementation.

|  |  |
| --- | --- |
| STRENGTHS (+)   * Improving accessibility could potentially open the system to a wider audience in the future. | WEAKNESSES (-)   * Increase in project costs and time due to modifications to all interfaces, as the team lacks experience in implementing accessible interfaces. * Possible introduction of errors in the current system interfaces due to the changes. |
| OPPORTUNITIES (+)   * Could set a positive precedent for future accessibility updates in other projects. | THREATS (-)   * High development cost for a perceived limited benefit, given that the system is mainly used by doctors (a low percentage with visual impairments) and not by patients (who may have a slightly higher percentage). * Possible need for additional training for current users due to the interface changes. |

5.3.2 Technical Evaluation

The change request affects the following configuration items:

1. Requirements Specification Document: All system interfaces must be modified, which involves defining new functional prototypes and design styles to meet the accessibility to visual debils.
2. Source Code: the CSS and HTML and JavaScript styles must be reimplemented.
3. Acceptance Testing Document: All test cases are modified to validate the modifications in the interfaces as defined in the new visual design.

This change impacts the baseline, causing an impact on the duration and final cost of the project.

* The duration of the project will be extended by 2 month (40 Work days).
  + Initial duration after accepted Change Request #2: 5.5 months (110 working days).
  + Additional time: 2 month (Represents **36%** of the initial duration).
  + Current project duration: 5.5 months + 2 months = **7.5 months (150 Work days).**

The following table details the calculation of the time needed to develop Change Request #3.

-As the project team has no knowledge of the specifications that must be met by the interfaces for the visual debils, it is necessary to hire an expert graphic designer in this area.

- The graphic designer has specified that it needs 1 month to be able to carry out the revision of the current system and to be able to design the style of the new interfaces.

Time of the development team to develop modifications to the interfaces:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Functionalities** | **Requirements Specification Document** | **System Design Document** | **Source code** | **Acceptance Testing Document** |
| **Time (Days)** | | | |
| All Interfaces of the system. | 4 | 2 | 10 | 4 |
| **Change request #3** | **20 Days**  **(1 month)** | | | |

* The cost of the project will increase, it is necessary to pay 40 more days of work to the team and contract the services of an external company.
  + Initial project cost after accepted change request #2: 354200 MXN.
  + Additional cost: 71200 MXN (Represents **20%** of the initial cost).
    - 55200 MXN: Cost to develop interface modifications by the development team.
    - 16000 MXN: Cost to hire the external graphic designer.
  + Current project cost: 354200 MXN + 71200 = **425400 MXN**.

The following tables detail the additional cost calculation associated with Change Request #3.

|  |  |  |  |
| --- | --- | --- | --- |
| **Roles** | **Configuration items** | **Daily Salary  (Mexican coin)** | **Change request #1 (Days - Salary)** |
| Analyst | Requirements Specification Document | 2000 MXN | 4 Day  8000 MXN |
| Architect | System Design Document | 2700 MXN | 2 Days  5400 MXN |
| Developer | Source code | 2500 MXN | 10 Days  25000 MXN |
| Tester | Acceptance Testing Document | 1900 MXN | 4 Days  7600 MXN |
| Total Salary | | | 46000 MXN |
| 20 %  Other expenses (Electricity, Rent, Office Supplies and other expenses) | | | 9200 MXN |
| **Total Additional Cost** | | | **55200 MXN** |

5.3.3 Evaluation of Change Request

|  |  |  |
| --- | --- | --- |
| **Criteria** | **Levels** | **Evaluation** |
| Impact on the business | Low (1) | Sum: 5  **Rejected** |
| Limited impact on the business, as the system will be used mainly by doctors, not by patients with visual disabilities. Improved accessibility of screens does not contribute significantly to the main functionality of the system or the operational efficiency of doctors. |
| Urgency of change | Low (1) |
| All system interfaces need to be modified. Requires adjustments to fonts, colors and descriptions with sound. The extent of the work required makes it technically complex |
| Technical Complexity | High (1) |
| Implementing a Kerberos-like authentication method is technically challenging. Kerberos is a complex protocol that requires a deep understanding of security. |
| Cost Associated | Medium (2) |
| Represents 20% of the initial cost.   * Initial project cost after accepted change request #2: 354200 MXN * Additional cost: 71200 MXN   Represents 36% of the initial duration.   * Initial duration after acceptance of change request #2: 5.5 months * Additional time: 2 months |

5.4 Change request #4

The client requests that the system incorporate new features for psychiatric patients. This implies new requirements, such as monitoring patients' medication histories, admitting them to the hospital, and performing medical interventions during psychiatric crises.

5.4.1 Strategic Evaluation

The SWOT matrix is used to identify and assess the Strengths, Weaknesses, Opportunities, and Threats associated with the change request. The matrix provides a comprehensive view of the internal and external factors that may influence the success of the change request implementation.

|  |  |
| --- | --- |
| STRENGTHS (+)   * Experience of the team in the development of modules related to mental health. * The system already has a flexible structure that allows the addition of new modules and functionalities. | WEAKNESSES (-)   * Increasing the scope of the project may increase the risk of errors in existing modules. |
| OPPORTUNITIES (+)   * It can significantly improve the quality of psychiatric care and patient satisfaction. * Possibility of expanding the system to new areas of mental health (psychiatric care). | THREATS (-)   * Additional regulations and legal requirements in the treatment and handling of psychiatric patient data. |

5.4.2 Technical Evaluation

The change request affects the following configuration items:

1. The Requirements Specification Document: new functionalities will be added (Obtaining statistics associated with types of attention and patient follow-up).
   * Implement new modules that allow hospital management corresponding to the period of admission of patients (management of clinical history, examinations performed, drugs supplied). In addition, new statistics associated with the treatment of patients admitted for psychiatric crises need to be incorporated.The System Design Document: new classes must be created for subsequent implementation.
2. Source code: New classes with their methods must be implemented.
3. Database: New tables and their relationships corresponding to the new modules to be implemented.
4. Acceptance Testing Document: New test cases must be designed to validate the new functionalities.

This change impacts the baseline, causing an impact on the duration and final cost of the project.

* The duration of the project will be extended by 2 month (40 Work days).
  + Initial duration after accepted Change Request #2: 5.5 months (110 working days).
  + Additional time: 2 month (Represents **36%** of the initial duration).
  + Current project duration: 5.5 months + 2 months = **7.5 months (150 Work days).**

The following table details the calculation of the time needed to develop Change Request #3.

-As the project team has no knowledge of the specifications that must be met by the interfaces for the visual debils, it is necessary to hire an expert graphic designer in this area.

- The graphic designer has specified that it needs 1 month to be able to carry out the revision of the current system and to be able to design the style of the new interfaces.

Time of the development team to develop modifications to the interfaces:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Functionalities** | **Requirements Specification Document** | **System Design Document** | **Source code** | **Acceptance Testing Document** |
| **Time (Days)** | | | |
| All Interfaces of the system. | 4 | 2 | 10 | 4 |
| **Change request #3** | **20 Days**  **(1 month)** | | | |

* The cost of the project will increase, it is necessary to pay 40 more days of work to the team and contract the services of an external company.
  + Initial project cost after accepted change request #2: 354200 MXN.
  + Additional cost: 71200 MXN (Represents **20%** of the initial cost).
    - 55200 MXN: Cost to develop interface modifications by the development team.
    - 16000 MXN: Cost to hire the external graphic designer.
  + Current project cost: 354200 MXN + 71200 = **425400 MXN**.

The following tables detail the additional cost calculation associated with Change Request #3.

|  |  |  |  |
| --- | --- | --- | --- |
| **Roles** | **Configuration items** | **Daily Salary  (Mexican coin)** | **Change request #1 (Days - Salary)** |
| Analyst | Requirements Specification Document | 2000 MXN | 4 Day  8000 MXN |
| Architect | System Design Document | 2700 MXN | 2 Days  5400 MXN |
| Developer | Source code | 2500 MXN | 10 Days  25000 MXN |
| Tester | Acceptance Testing Document | 1900 MXN | 4 Days  7600 MXN |
| Total Salary | | | 46000 MXN |
| 20 %  Other expenses (Electricity, Rent, Office Supplies and other expenses) | | | 9200 MXN |
| **Total Additional Cost** | | | **55200 MXN** |

5.4.3 Evaluation of Change Request

|  |  |  |
| --- | --- | --- |
| **Criteria** | **Levels** | **Evaluation** |
| Impact on the business | Low (1) | Sum: 5  **Rejected** |
| Limited impact on the business, as the system will be used mainly by doctors, not by patients with visual disabilities. Improved accessibility of screens does not contribute significantly to the main functionality of the system or the operational efficiency of doctors. |
| Urgency of change | Low (1) |
| All system interfaces need to be modified. Requires adjustments to fonts, colors and descriptions with sound. The extent of the work required makes it technically complex |
| Technical Complexity | High (1) |
| Implementing a Kerberos-like authentication method is technically challenging. Kerberos is a complex protocol that requires a deep understanding of security. |
| Cost Associated | Medium (2) |
| Represents 20% of the initial cost.   * Initial project cost after accepted change request #2: 354200 MXN * Additional cost: 71200 MXN   Represents 36% of the initial duration.   * Initial duration after acceptance of change request #2: 5.5 months * Additional time: 2 months |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Functionalities** | **Requirements Specification Document** | **System Design Document** | **Source code** | **Acceptance Testing Document** |  |
| **Time (Days)** |  |  |  |  |  |
| Module Reports  (Obtain statistics on mental disorders) | 2 | 1 | 1 | 2 |  |
| Module Security  (Adjust the implementation of System authentication to be similar to the Kerberos method) | 3 | 1 | 1 | 4 |
| **Change request #120 Days**  **(1 month)** | 1 | 4 | 3 | 10 | 2 |
|  |  |  |  |  |  |